Organization/Site:

Identified Lead:

| Roles/Tasks | Actionable Items/Examples* | Current Status/Potential Barriers/Notes | # Plan (including timeframe) | Who’s in Charge? | Metrics and How you define success for each item |
| --- | --- | --- | --- | --- | --- |
| Determine Who to Receive CC | - Identify population to receive CC - Any other CC program? |  |  |  | 1. Confirm proposed target population. 2. Confirm how this population will be identified (inclusion criteria) 3. Caring Contacts SOP and Tracking Process Training |
| Determine Who Administers | - Method to administer CC - Determine who administers - MSA or PSA - Health tech - Social worker - Other |  | The person who administers CC (sending and documenting) may need access to the electronic medical record. |  | Caring Contacts Roles Filled |
| Determine Start Date | - Identify start date for the implementation of this plan. - It is ok change the start date after it was selected due to kinks in the plan. |  | We recommend doing this ASAP after beginning to develop your plan. |  | Target date to begin identifying suicidal recipients and initiate mailings set. |
| Determine Schedule of CC | - Consider the length, principles of non-demanding messages, and your audience - See recommended CC schedules |  |  |  |  |
| Determine Content of Caring Contacts | - Use existing CC templates - Author or signature of CC - Nurse - Social worker - Physician - Care team - Combination - Local contact information/ phone numbers (required) - Dedicated phone line & mailbox? - Consider administrative requirements such as branding or logos |  | We strongly recommend using existing CC templates for messages that were developed with expert input to be appropriate for outreach. Do not include messages that are a demand (e.g., please call us, attend your appointments). You should put a number to call if someone would like to reach out (e.g., we are available if you need assistance). Handwritten messages are not needed, per research. |  |  |
| Determine Logistics of Sending CC | - Establish process for enrolling recipient to the chosen platform with their correct contact information - For texting: - Identify platform and establish terms of use - For mailing: - Utilize return address on card - Identify local standards for mailing. - Determine capacity for mailing and providing postage for greeting card envelopes - Identify resources and processes for printing |  | Identify resources and processes for printing and mailing Coordinate printing and mailing with mail room/reproduction Secure mailing supplies (envelopes, labels) Complete any tasks related to the SOP (e.g., mail merge training) Review documentation plan with relevant leadership, risk management, etc. |  | Mechanism in place with appropriate administrative and budget offices to obtain Caring Contacts materials (printed cards, envelopes, and labels). Documentation plan approved by all relevant parties |
| Determine What Needs to be Documented | - Method of documentation - Local note template - Identify who will document - Person managing/printing/mailing CC - Provider - Other clinical staff - Administrative support - Other - When will documentation happen - When CC is sent/mailed |  | We strongly recommend that the person printing/mailing the CC document when the card is prepared and mailed. This will allow them to see any relevant changes in CPRS. Documentation of each CC contact in medical record may be required. |  | - Process reviewed. - Process training completed. - Process integrated into workflow. |
| Engage & Train Staff, Assign Roles | - Determine which staff will be involved in Implementation Planning process (a meeting to complete the rest of this sheet). - Educate all staff through meetings and communications. - In-services with nursing staff - See section K for aligning with other CC programs. - Continue to engage and educate leadership. - Ensure all staff completes all brief CC training as needed. Training includes rationale for CC, how recipients are identified, and local SOPs. |  | We recommend that staff is trained prior to your start date. Include all relevant team members including ED, mental health, and primary care staff. |  | Key services/staff are trained. |
| Identify & Enroll Individuals | - Based on the inclusion criteria decided on previously |  |  |  |  |
| Start intervention | - According to the message schedule previously decided on - Monitor outgoing messages to ensure that they are delivering correctly |  |  |  | - First set of recipients identified. - Messages are sent/Cards are mailed. - Messages are documented as needed |
| Respond to Recipients’ Replies | - Review the suggested responses based on message content |  |  |  |  |
| Manage responses indicating crisis | - Follow the protocols required by your organization, or |  |  |  |  |
| Ending the intervention | - Ensure that recipients are made aware that the program is ending - Proceed with post-intervention procedures previously decided on (offering to continue the messages, offering an exit interview or final check-in) - Request that recipients complete a reception survey |  | Consider using the feedback survey provided on caringcontacts.info |  |  |
| Reporting Caring Contacts Use | - Identify reports to document number of recipients served by CC - Review and report on feedback obtained from reception survey |  |  |  |  |
| If applicable to your organization: Align with Other Caring Contacts Programs | - Determine what other CC programs exist within your organization - Ensure that CC efforts are not duplicated or that identical messages are not sent to the same recipient from the different CC programs |  | Determine if and how your facility will address multiple CC programs. Note: Recipients may be enrolled in other CC programs independent from your organization. |  |  |

Suggested items to review for transitioning tasks during team turnover:

| PROCESS SUSTAINMENT PLAN |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Identification of recipients | CC Message Sending Mgmt | CC Card Mailing | Caring Contacts Tracking Update | Caring Contacts Documentation | Ongoing Caring Contacts Card Counts | Caring Contacts Ongoing Education | Caring Contacts Funding |
| Responsible Person |  |  |  |  |  |  |  |  |

| TRANSITION PLAN | Review Date |
| --- | --- |
| Review process of identifying recipients |  |
| Review use of Caring Contacts Tracker spreadsheet (duplicates, excluded individuals, etc.) |  |
| Review Documentation plan |  |
| Review Sending Processes |  |
| Review Reporting Processes |  |